## Overview
HDI Workshop Studio — Dev Tracker
Companion to docs/workshop/PRD.md and ROADMAP.md. Update Status columns in Development and Testing sheets; this sheet computes itself.
Phase | Name | Dev tasks | Dev done | Dev progress | Tests | Tests passed | Test progress
1 | Accounts, planner, idea bank
2 | Templates, renderer, player, print
3 | AI generation
4 | Participant interaction
5 | Polish (optional)
TOTAL
Note: Phase 5 test cases are defined when each polish task is scheduled (see ROADMAP.md).

## Development
ID | Phase | Task | File(s) | Depends on | Status | Notes
D1.1 | 1 | Router with auth + blob sync | tools/workshop.js | — | Not started | Copy tools/poker.js: users/user_data/user_snapshots schema, requireAuth, signup/login (bcrypt 12), rev'd GET/PUT /data with 409+authoritative state, snapshots
D1.2 | 1 | Frontend scaffold + brand chrome | static/workshop/index.html, styles.css, src/api.js | D1.1 | Not started | Hash-route SPA shell; HDI brand vars (#BD0129/#8E011F/#51000C), Merriweather + Be Vietnam Pro, logo asset
D1.3 | 1 | Sync store (DataProvider port) | static/workshop/src/store.js | D1.1 | Not started | Vanilla port of hdpg-poker.html DataProvider (~lines 3186-3330): 800ms debounce, pagehide flush, adopt-server-on-409
D1.4 | 1 | Auth screens | static/workshop/src/planner.js | D1.2 | Not started | Login/signup forms; JWT in localStorage
D1.5 | 1 | Seeds module + merge | static/workshop/src/seeds.js | D1.3 | Not started | planItemTypes (FR-2.5), ideaBank (PRD App. A, ~34 entries), interactionTemplates (App. C), seedVersion merge
D1.6 | 1 | Dashboard + DEFINE block | static/workshop/src/planner.js | D1.4 | Not started | Workshop cards, create/duplicate/delete (snapshot first), DEFINE form (FR-1.1)
D1.7 | 1 | Run-sheet | static/workshop/src/planner.js | D1.6 | Not started | Sections, type badges, inline edit, item detail panel, HTML5 drag reorder, live timing math (FR-2.3)
D1.8 | 1 | Item type manager | static/workshop/src/planner.js | D1.7 | Not started | CRUD taxonomy: name, category S/A/structural, color
D1.9 | 1 | Idea bank UI | static/workshop/src/planner.js | D1.5 | Not started | Browse/search/filter, CRUD+duplicate, add-to-plan (copy, keeps bankRef), save-to-bank
D1.10 | 1 | Homepage card | static/index.html | D1.2 | Not started | Card linking to /workshop/, existing card markup
D2.1 | 2 | Renderer | static/workshop/src/renderer.js | D1.5 | Not started | PRD §4.4 pipeline: {{key}} substitution, marked (esm.sh) for markdown, data-list, computed context, data-step(+auto), CSS scoping, JS hook loader
D2.2 | 2 | Built-in slide templates (13) | static/workshop/src/seeds.js | D2.1 | Not started | PRD App. B #1-11 and #18; hand-authored + previewed
D2.3 | 2 | Renderer contract doc | docs/workshop/renderer-contract.md | D2.1 | Not started | Written alongside D2.1; becomes the Phase 3 prompt verbatim
D2.4 | 2 | Slide CRUD + attachment flow | static/workshop/src/editor.js | D2.1 | Not started | Rail grouped by plan item; create requires attach-or-create-item (FR-5.1); delete item prompts delete/re-attach
D2.5 | 2 | Field-form editor + preview | static/workshop/src/editor.js | D2.4 | Not started | Schema-driven forms (text/markdown/number/select/image/list), live preview, speaker notes
D2.6 | 2 | Template manager | static/workshop/src/templates.js | D2.2 | Not started | Schema builder + HTML/CSS/JS tabs (CodeMirror 6 lazy, textarea fallback) + preview; edits re-render dependent slides
D2.7 | 2 | Deck player — present mode | static/workshop/present.html, src/player.js | D2.2 | Not started | Deck=flatten(items→slides), keyboard nav, deterministic steps, item countdown + overrun, schedule bar, notes drawer, overview grid
D2.8 | 2 | Read/print mode | static/workshop/src/player.js, styles.css | D2.7 | Not started | ?mode=read: linear, headings, all steps expanded, print CSS (page/slide, footer), R toggle
D3.1 | 3 | Anthropic SDK + config | package.json, tools/workshop.js | D2.3 | Not started | npm i @anthropic-ai/sdk; ANTHROPIC_API_KEY (fly secrets); model const claude-sonnet-5; no temperature; 503 when key missing
D3.2 | 3 | POST /generate-slides | tools/workshop.js | D3.1 | Not started | Cached stable prefix (renderer-contract + brand), schema validation + 1 retry, ai_generations log, daily cap 100 → 429
D3.3 | 3 | POST /generate-template | tools/workshop.js | D3.1 | Not started | Description → template JSON, shape-validated; human previews before save
D3.4 | 3 | Generation dialog | static/workshop/src/editor.js | D3.2 | Not started | Per item: count + template per slide + instruction → review list, accept/regenerate/discard per slide
D3.5 | 3 | Edit-via-prompt | static/workshop/src/editor.js | D3.2 | Not started | Instruction + current fields → revised fields; before/after preview; apply/discard
D3.6 | 3 | Template generation UI + usage display | static/workshop/src/templates.js | D3.3 | Not started | AI draft opens in editor unsaved; GET /usage: month spend estimate + today count
D4.1 | 4 | Session tables + endpoints | tools/workshop.js | D2.1 | Not started | live_sessions/responses DDL (PRD §4.2), endpoints (§4.3), snapshot publish, payload validation + size caps + rate limit, unambiguous code alphabet
D4.2 | 4 | Participant page | static/workshop/join.html, src/participant.js | D4.1 | Not started | Mobile-first, ?c=CODE, localStorage participant id, 2s poll, native inputs for 4 kinds, waiting/ended states
D4.3 | 4 | Interactive slide templates | static/workshop/src/seeds.js, renderer.js | D4.1 | Not started | App. B #12-17 with onResults: bars, word cloud, avg+distribution, dot overlay, cards; interaction field type in editor
D4.4 | 4 | Player session controls | static/workshop/src/player.js | D4.2, D4.3 | Not started | Start/end session, QR + code badge, activate on interactive slides, results polling → onResults, quiz reveal step
D4.5 | 4 | Load-test script | scripts/workshop-participant-sim.js | D4.2 | Not started | N simulated participants (default 30) join + respond; assert 2xx + final counts
D5.1 | 5 | custom-html escape hatch | seeds.js, renderer.js | D2.1 | Not started | Sandboxed iframe (allow-scripts), mode/step via postMessage
D5.2 | 5 | CSV export of session responses | tools/workshop.js | D4.1 | Not started | GET /sessions/:code/export (auth) → CSV; addresses R7
D5.3 | 5 | Workshop JSON export/import | static/workshop/src/planner.js | D1.7 | Not started | Blob-slice download/upload; systems-explorer downloadJson pattern
D5.4 | 5 | Paste-from-Sheets import | static/workshop/src/planner.js | D1.7 | Not started | Paste TSV (Topic/Key Ideas/Time/Type) → parsed items with type-mapping preview
D5.5 | 5 | /j/:code short URL | server.js | D4.1 | Not started | One redirect line
D5.6 | 5 | Snapshot restore UI | static/workshop/src/planner.js | D1.3 | Not started | Browse/restore user_snapshots (endpoints exist)

## Testing
ID | Phase | Test case | Steps | Expected | Status | Notes
T1.1 | 1 | Auth round-trip | Sign up new user; log out; log back in; try wrong password; try duplicate username | Login works; wrong password rejected; duplicate username → 409 message | Untested
T1.2 | 1 | Workshop persistence cross-device | Create workshop with full DEFINE block; reload; open in second browser profile | Identical state in both; nothing lost on reload | Untested
T1.3 | 1 | Two-tab conflict safety | Open two tabs; edit different fields in both quickly | Stale tab gets 409-handled: adopts server state, no data loss, no crash | Untested
T1.4 | 1 | Timing math | Add 2 sections + 6 items with durations and types | Section subtotals, total, over/under-target delta, per-item clock times all correct | Untested
T1.5 | 1 | Drag reorder | Drag item to another section; drag a section above another; reload | Order + subtotals update; section moves its block; persists | Untested
T1.6 | 1 | Custom item type | Add type with custom color in type manager; assign to an item | Appears in dropdown; badges row with its color | Untested
T1.7 | 1 | Idea bank copy semantics | Search 'brainwriting'; Add to plan; then edit the bank entry | Plan item pre-filled; later bank edit does NOT change the inserted item | Untested
T1.8 | 1 | Pagehide flush | Edit a field and immediately kill the tab (within debounce window); reopen | Change survived (keepalive flush) | Untested
T2.1 | 2 | Built-in templates render | Preview all 13 built-in templates with sample data in editor | Each renders correctly, brand fonts/colors, no console errors | Untested
T2.2 | 2 | No orphan slides | Create slide via item '+' and via global new-slide dialog | Both paths force attachment (existing item or new item inline); orphan impossible | Untested
T2.3 | 2 | Step reveals deterministic | Bullets slide with 4 bullets: step through, back-arrow, jump from overview grid | One bullet per keypress; back works; jump lands with correct step state | Untested
T2.4 | 2 | Plan→deck sync | Reorder plan items; retime an item with an instructions slide | Deck order follows immediately; slide shows new duration without editing the slide | Untested
T2.5 | 2 | Timer behavior | Present an item with durationMin set; let it overrun; move to next item | Counts down, turns red on overrun, resets on item change | Untested
T2.6 | 2 | Read mode + print | Toggle R; Chrome print preview; save PDF | All reveals expanded, headings between groups; one slide per page, no clipping; PDF opens | Untested
T2.7 | 2 | Template edit propagation | Duplicate a builtin, change CSS, save; edit a template's HTML | Only the copy's slides change; HTML edit re-renders all dependent slides | Untested
T2.8 | 2 | Agenda auto-feed | Add agenda slide; change plan sections/durations | Agenda reflects live sections + subtotals on next render | Untested
T3.1 | 3 | Graceful no-key state | Unset ANTHROPIC_API_KEY; open generation dialog | Clear 'AI unavailable' message; rest of app fully functional | Untested
T3.2 | 3 | Generate slides | Generate 3 slides (bullets, big-number, debrief) for a real item; once with Vietnamese content | All validate against schemas, render without hand-fixing, correct language | Untested
T3.3 | 3 | Regenerate with refinement | Regenerate one reviewed slide with a refinement instruction; accept | Only that slide changes; accepted slide attached to right item in order | Untested
T3.4 | 3 | Edit-via-prompt precision | Ask to change one aspect of an existing slide | Exactly the requested aspect changes in fields | Untested
T3.5 | 3 | Generate template | Describe 'myth vs fact two-panel with reveal' | Draft previews with sample data; after save usable on a new slide | Untested
T3.6 | 3 | Caps + logging | Set cap override to 2; make 3 calls; check /usage | Third call → 429 surfaced politely; tokens logged in ai_generations; usage sums match | Untested
T4.1 | 4 | Session join | Start session; scan QR with a real phone | Code + QR on player; phone joins without login | Untested
T4.2 | 4 | Poll live round-trip | Activate poll; vote; re-vote; deactivate | Bar updates ≤2s; re-vote replaces (count unchanged); deactivate freezes results, phone shows waiting | Untested
T4.3 | 4 | Word cloud + XSS probe | 3+ phones submit words; one submits '<img src=x onerror=alert(1)>' | Cloud scales by frequency; probe renders as inert text (text nodes only) | Untested
T4.4 | 4 | Quiz reveal | Run quiz slide: vote, then advance to reveal step | Votes hidden until reveal; reveal shows distribution + highlights correct answer | Untested
T4.5 | 4 | Rating + hotspot kinds | Run rating and hotspot slides end-to-end on a phone | Both submit and render aggregates (avg+distribution; dot overlay) | Untested
T4.6 | 4 | Snapshot isolation | Edit the workshop while a session is live | Live session unaffected (published snapshot) | Untested
T4.7 | 4 | Load test | node scripts/workshop-participant-sim.js 30 | Zero errors, counts correct, player stays smooth | Untested
T4.8 | 4 | Session end state | End session; open join page; open read mode | Join page says session ended; results still visible in read mode | Untested